## Task Status
Tasks | Status | Tentative Completion Date | Comments
VBCS Pages
Create Invoice Page | Done | 2020-11-16 | Except below which are dependant on blockers: Invoice Ref Defaulting Filtering bill to loc based on customer Default Approvers based on requestor
Create Invoice Line Page | Done | 2020-11-16
Edit Invoice Line Page | Done | 2020-11-16
Delete Invoice Line Page | Done | 2020-11-16
Create Invoice Distributions Page | Done | 2020-11-16
Edit Invoice Distributions Page | Done | 2020-11-16
Delete Invoice Distributions Page | Done | 2020-11-16
Search Invoices Page | Done | 2020-11-16
Update Invoices Page | Done | 2020-11-16
Delete Invoices | Done | 2020-11-16
Duplicate Invoice Functionality | Not Started
Approval Notifications Page | Not Started
Sync VBCS Page | Not Started
PCS Approval Process
Main Approval Process with below logic | WIP | 2020-11-23 | Normal Invoice
Req -> Req Mgr -> GSTTIDM/Alex -> AR Invoice Service
Credit Note
Req -> Req Mgr -> GSTTIDM/Alex -> CFO (Amt>100k) -> AR Invoice Service
Configure Notification Templates & Settings | WIP | 2020-11-23
Integration
ICS - AR Invoice Service | Not Started |  | Service to interface data to ERP
Code Combination Validation Service | Not Started |  | This needs to be discussed further
Prepare Unit Test Script and Capture Results | Not Started
IDCS Configuration - Load 350 users & assign roles |  |  | This will be handled by Version1
Data Sync from ERP Cloud to VBCS BO |  |  | This will be handled by Version1
BIP Reports |  |  | This will be handled by Version1
ICS - Other ERP Data Sync Service |  |  | This will be handled by Version1
ICS - Revenue Account Sync Service |  |  | This will be handled by Version1

## Technical Blockers
Technical Blockers | Comments
VBCS database change to ADW/ATP Database | Praveen has raised an SR for this
Creating 3 procedures and exposing them as REST API's | Praveen to create and share the details