## Task Status
Tasks | Status | Tentative Completion Date | Comments
VBCS Pages
Create Invoice Page | Done | 2020-11-16 | Pending Filtering bill to loc based on customer
Create Invoice Line Page | Done | 2020-11-16
Edit Invoice Line Page | Done | 2020-11-16
Delete Invoice Line Page | Done | 2020-11-16
Create Invoice Distributions Page | Done | 2020-11-16 | Pending Distribution decimal amount error
Edit Invoice Distributions Page | Done | 2020-11-16
Delete Invoice Distributions Page | Done | 2020-11-16
Search Invoices Page | Done | 2020-11-16
Update Invoices Page | Done | 2020-11-16
Delete Invoices | Done | 2020-11-16
Duplicate Invoice Functionality | Done | 2020-11-22
Approval Notifications Page | Not Started
Sync VBCS Page | Not Started |  | Blocked Dependent on data sync component build by Version1
PCS Approval Process
Main Approval Process with below logic | Done | 2020-11-22 | Normal Invoice => Req -> Req Mgr -> GSTTIDM/Alex -> AR Invoice Service Credit Note => Req -> Req Mgr -> GSTTIDM/Alex -> CFO (Amt>100k) -> AR Invoice Service
Configure Notification Templates & Settings | Done | 2020-11-22
Integration
ICS - AR Invoice Service | WIP | 2020-11-29 | Service to interface data to ERP
ICS - AR Invoice Callback Service | Not Started
Code Combination Validation Service | Not Started |  | This needs to be discussed further
Prepare Unit Test Script and Capture Results | Not Started
IDCS Configuration - Load 350 users & assign roles |  |  | This will be handled by Version1
Data Sync from ERP Cloud to VBCS BO |  |  | This will be handled by Version1
BIP Reports |  |  | This will be handled by Version1
ICS - Other ERP Data Sync Service |  |  | This will be handled by Version1
ICS - Revenue Account Sync Service |  |  | This will be handled by Version1

## Technical Blockers
Technical Blockers | Comments | Status
VBCS database change to ADW/ATP Database | Praveen has raised an SR for this 22-Nov-16: Issue resolved and DB Change done | Resolved
Creating 3 procedures and exposing them as REST API's | Praveen to create and share the details 22-Nov-16: Created REST APIs and was able to use them in VBCS App | Resolved