## Task Status
Tasks | Status | Tentative Completion Date | Comments
VBCS Pages
Create Invoice Page | Done | 2020-11-16 | Pending Filtering bill to loc based on customer
Create Invoice Line Page | Done | 2020-11-16
Edit Invoice Line Page | Done | 2020-11-16
Delete Invoice Line Page | Done | 2020-11-16
Create Invoice Distributions Page | Done | 2020-11-16 | Pending Distribution decimal amount error
Edit Invoice Distributions Page | Done | 2020-11-16
Delete Invoice Distributions Page | Done | 2020-11-16
Search Invoices Page | Done | 2020-11-16
Update Invoices Page | Done | 2020-11-16
Delete Invoices | Done | 2020-11-16
Duplicate Invoice Functionality | Done | 2020-11-22
Approval Notifications Page | Not Started | 2020-12-07
Sync VBCS Page | Not Started | 2020-12-07 | Blocked Dependent on data sync component build by Version1
PCS Approval Process
Main Approval Process with below logic | Done | 2020-11-22
Configure Notification Templates & Settings | Done | 2020-11-22 | There was a request to print invoice details with in notification email body. In OIC Dev Instance, images are not getting printed inline. Praveen has raised a Sev1 SR and following up with Oracle on this.
Integration
ICS - AR Invoice Service | Done | 2020-11-29 | Build complete and Invoice getting interfaced to ERP Cloud. However Auto Invoice Import failing with sequencing related error. We will not have this error if Invoice Request is created with actual data from ERP cloud after sync build is done
ICS - AR Invoice Callback Service | WIP | 2020-12-01 | Callback service to communicate invoice creation status to concerned people and update status back on VBCS app
Prepare Unit Test Script and Capture Results | Not Started | 2020-12-07
IDCS Configuration - Load 350 users & assign roles |  |  | This will be handled by Version1
Data Sync from ERP Cloud to VBCS BO |  |  | This will be handled by Version1
BIP Reports |  |  | This will be handled by Version1
ICS - Other ERP Data Sync Service |  |  | This will be handled by Version1
ICS - Revenue Account Sync Service |  |  | This will be handled by Version1

## Technical Blockers
Technical Blockers | Comments | Status
VBCS database change to ADW/ATP Database | Praveen has raised an SR for this 22-Nov-16: Issue resolved and DB Change done | Resolved
Creating 3 procedures and exposing them as REST API's | Praveen to create and share the details 22-Nov-16: Created REST APIs and was able to use them in VBCS App | Resolved
Images not getting printed in PCS notifications | There was a request to print invoice details with in notification email body. In OIC Dev Instance, images are not getting printed inline. Praveen has raised a Sev1 SR and following up with Oracle on this. | Pending