## Revised Effort Estimate
Tasks | Rough Estimate (In Hours) | Comments
IDCS Configuration - Load 350 users and assign appropriate roles | 0
VBCS Pages
Create Invoice Page | 40 | Invoice and it's lines should be displayed on the same page unless there is an explicit reason
Create Invoice Line Page | 16
Search Invoices Page | 16 | Ability to search for Invoice by Ref, Amount, Status, Customer, Requestor, Last Update
Update Invoices Page | 8
Duplicate Invoice Functionality | 24
Delete Invoices | 8
Landing Page | 24
Sync VBCS Page | 16
PCS Approval Process
Main Approval Process with below logic | 56 | Normal Invoice
Req -> Req Mgr -> GSTTIDM/Alex -> AR Invoice Service
Credit Note
Req -> Req Mgr -> GSTTIDM/Alex -> CFO (Amt>100k) -> AR Invoice Service
Configure Notification Templates & Settings | 24
Configure Approvers | 0 | This might or might not be required
Integration
ICS - AR Invoice Service | 40 | Service to interface data to ERP | OIC Invoice Interface | 40
Code Combination Validation Service | 24
Data Sync from ERP Cloud to VBCS BO
BIP Reports | 0 | This entire piece will be handled by Version1 | Reports | 32
ICS - Other ERP Data Sync Service | 0 |  |  | 40
ICS - Revenue Account Sync Service | 0 |  |  | 24
Prepare Unit Test Script and Capture Results | 40
Total Hours | 336