## Sheet1
Tasks | Comments
IDCS Configuration - Load 350 users and assign appropriate roles | This entire piece will be handled by Version1
VBCS Pages
Create Invoice Page | Invoice and it's lines should be displayed on the same page unless there is an explicit reason
Create Invoice Line Page
Search Invoices Page | Ability to search for Invoice by Ref, Amount, Status, Customer, Requestor, Last Update
Update Invoices Page
Duplicate Invoice Functionality
Delete Invoices
Landing Page
Sync VBCS Page
PCS Approval Process
Main Approval Process with below logic | Normal Invoice
Req -> Req Mgr -> GSTTIDM/Alex -> AR Invoice Service
Credit Note
Req -> Req Mgr -> GSTTIDM/Alex -> CFO (Amt>100k) -> AR Invoice Service
Configure Notification Templates & Settings
Configure Approvers | This might or might not be required
Integration
ICS - AR Invoice Service | Service to interface data to ERP
Code Combination Validation Service
Data Sync from ERP Cloud to VBCS BO
BIP Reports | This entire piece will be handled by Version1
ICS - Other ERP Data Sync Service
ICS - Revenue Account Sync Service
Prepare Unit Test Script and Capture Results
Fixed Cost to deliver above components by 07-Nov-20 (This includes only Dev and Unit Testing cost) | 393750 INR